## CFA
Calculation of CFA
Principle
| Podium CFA | Site area x site coverage
| Total GFA | Site area x plot ratio
CFA : GFA
| Residential (apartment) | 1.15-1.25 (1.15)
| Residential (house) | 1.2-1.3 (1.25)
| Office / Commercial | 1.15-1.2 (1.2)
| Hotel | 1.3-1.4 (1.35)
| Industrial | 1.15-1.2 (1.2)
| Government | 1.15-1.25
| Refuge floor | 1.03
Unit
| m : ft | 3.28
| m2 : ft2 | 10.76
| Steel | 7843 kg/m3
Other
| Carpark | 1 No. per 2 flats
| Carpark (basement) | 40-50m2/No. incl. driveway & ramp
| Carpark (open) | 25 m2/No. incl. driveway
| Loading & unloading bay | 150m2 (3 x standard carpark)
| Clubhouse | <= 5% of GFA of residential portion
| Refuge floor | One floor for residential building over 25 storeys
| Hotel | FOH : Guest room : BOH = 15-20% : 50-60%: 25-30%
| Hotel | 55-100 m2/room
| Office | 9m2 / person
| Hospital | 60-120 m2/bed
| Auditorium | 1.5-2 m2/seat

## Qty & Rate
Major Rates Referemce
[5 empty] | Assumption | Qty | Unit | Rate | Cost/CFA | Remarks
Site Investigation | [8 empty] | 50
| Site investigation | [8 empty] | suject to number of boreholes and trial pits
Demolition and Hoarding | [8 empty] | 100
| Demolition |  |  |  |  | CFA | m2 | 1000 |  | including shoring
| Site clearance |  |  |  |  | site area | m2 | 200
| Hoarding |  |  |  | 2.5m high | perimeter of site; deduct length against adjoining building | m | 8000 |  | include making good of adjoining building / affected area
| Covered walkway | [5 empty] | m | 20000
Foundation and Basement |  |  |  |  | consider waterproof concrete |  |  |  | 4000
ELS and site formation
|  | Excavation, disposal and backfill |  |  |  |  | m3 | 500
|  | Monitoring works |  |  |  | site area | m2 | 200
Lateral support
Pipe pile
|  |  |  | Pipe pile | CHS 273mm dia; 400mm c2c | depth = 2 times of excavation | m | 3000
[5 empty] | 813mm dia |  | m | 10500
|  |  |  | Lagging wall | 12mm steel plate | depth = excavation | m2 | 2500
|  |  |  | Grout curtain | required / not required | depth = pipe pile | m2 | 2500
Sheet pile
|  |  |  | Sheet pile | 190kg/m2 | depth = 2 times of excavation | kg | 20
|  |  |  | Grout curtain | required / not required | depth = sheet pile | m2 | 2500
Diaphragm wall
|  |  |  | Disphragm wall | 1m thick; 40m deep |  | m3 | 8000
|  |  |  | Cavity wall | 150mm thick | basement perimeter x basement depth | m2 | 500
|  | Structting and shoring |  |  | 600kg/m2 on structting area | basement perimeter x basement depth | kg | 20
|  | Dewatering |  |  |  |  | item | 5% |  | allowance only
Raft foundation
|  | Excavation, disposal and backfill |  |  | open cut with working space 0.25m; 500mm thick + 1m below ground level |  | m3 | 500
|  | Raft footing |  |  | 500mm thick 45D formwork: no formwork to bottom; 0.1m2/m2 raft area rebar: 200kg/m3 | raft area = footprint area | m2 | 2050
|  | Waterproof tanking |  |  |  | 1m2/m2 raft area if not available | m2 | 500
|  | Binding layer |  |  | 50mm thick |  | m3 | 1400
|  | Miscellaneous |  |  | vapour barrier, hardcore, joints, openings for services, etc. |  | item | 10% |  | allowance only
Bored pile foundation
|  | Bored pile |  |  | 2.5m dia; 25m deep; no rock encountered | 1m2 cross section for 250m2 CFA | m3 | 14000 |  | 63,000/m
|  | Bored pile |  |  | 2.5m dia; 60m deep; no rock encountered | 1m2 cross section for 250m2 CFA | m3 | 16000 |  | 80,000/m
|  | Socketd H pile |  |  | 223kg/m; 25m deep; no rock encountered | 1 no. for 100m2 CFA | m | 10000
|  | Mini pile |  |  | 219mm dia; 25m deep; no rock encountered | 1 no. for 50m2 CFA | m | 8000
Substructure
|  | Excavation and disposal |  |  |  | depth = pile cap + basement + wearing slab + pile cap + assume 1.5m to group level | m3 | 500
|  | Binding layer |  |  |  |  | m2 | 125
|  | Pile cap |  |  |  | footprint area of tower + assumed small cap for podium
|  |  | Binding layer |  | 75mm thick |  | m3 | 1400
|  |  | Pile cap |  | 2m thick; 300kg/m3 |  | m3 | 5500
Basement
|  |  | Basement slab and beam |  | 500mm thick; 250kg/m3 | basment area | m2 | 2300
|  |  | Reinforced screen wall |  | 500mm thick; 250kg/m3 |  | m2 | 3300
|  |  | Cavity block wall |  | 100mm thick | same as screen wall | m2 | 600
|  |  | Wear slab |  | 500mm thick; 150kg/m3 | basment area | m2 | 1700 |  | on top of basement bottom slab w sub-soil drainage
|  |  | Waterproofing to screen wall |  |  | depth incl. basement, wearing slab, pile cap | m2 | 500
|  |  | Waterproofing to slab |  |  | +30% for sides of pile cap if any + to basement top slab if larger than G/F slab | m2 | 500
|  |  | Dewatering |  |  |  | item | 5% |  | Included in ELS
Superstructure
Carcase
|  | Structure - concrete | [6 empty] | 5400
|  |  | Concrete |  |  | 0.55m3/m2 CFA | m3 | 1600 |  | suspended slab: 1500-200mm structural wall: 200mm column: beam, staircase
|  |  | Formwork |  |  | 2.5m2/m2 CFA | m2 | 500
|  |  | Rebar |  |  | general: 160-250kg/m3 column: 300kg/m3 beam: 250kg/m2 slab/stair: 120kg/m3 wall: 200kg/m3 | kg | 13
|  |  | Miscellaneous |  |  |  | item | 5% |  | allowance only
|  |  | Transfer plate to tower |  | 3.5m thick; 400kg/m3 |  | m2 | 21000
|  |  | Mass fill concrete |  |  |  | m3 | 1400
|  | Structure - steel | [7 empty] | 120% higher than concrete
|  |  | Structural steel |  | steel ratio include connections | 150-200 kg/m2 CFA | kg | 40
|  |  | FRP coating to structural steel |  |  |  | item | 20% |  | allowance only
|  |  | Metal decking outside core |  |  | 0.85 m2/m2 CFA | m2 | 1000
|  |  | Concrete |  | slab 120mm thick; wall same as concrete design; beam replaced by steel; column 80% of concrete design; | 0.36 m3/m2 CFA; including core walls, column casing, topping on metal decking | m3 | 1600
|  |  | Formwork |  |  | 1.25 m2/m2 CFA | m2 | 500
|  |  | Rebar |  |  | 160kg/m3 | kg | 13
|  |  | Miscellaneous |  | sundries like water tanks, staircases, expansion jointe, etc. |  | item | 5% |  | allowance only
|  | Façade | [6 empty] | 5800
|  |  | In-situ RC wall |  | 150mm thick |  | m2 | 1600
|  |  | Precast RC wall |  | 150mm thick |  | m2 | 3600
|  |  | Glass wall |  |  |  | m2 | 10000
|  |  | Curtain wall |  |  |  | m2 | 8000
|  |  | Window |  |  |  | m2 | 5000
|  |  | Louvre |  |  |  | m2 | 7000
|  |  | Aluminium cladding |  |  |  | m2 | 6000
|  |  | Performance test |  |  |  | item | 40000 |  | allowance only
|  |  | Architectural features |  |  |  | item | 10% |  | allowance only
|  |  | Corrugated metal roof |  | incl. extra cost for pitched roof, projection, gutters, etc. |  | m2 | 4000
|  |  | Corrugated sheet wall panel system |  | incl. allowance for windows of minimal area |  | m2 | 3000
|  | Internal non-structural wall |  |  |  | residential: 0.9-1m2/m2 CFA |  |  | 200
|  |  | RC wall |  | 100mm thick | deduct slab thickness 150mm 100kg/m3 | m2 | 1400 |  | lift shaft, staircase, plant room, kitchen
|  |  | Block wall |  | 100mm thick |  | m2 | 750 |  | bedroom, bathroom
|  |  | Dry wall |  |  |  | m2 | 900
|  | Door and shutter |  |  |  | residential: 0.1 no./m2 CFA |  |  | 900
|  |  | Single timber door |  |  |  | no | 8000
|  |  | Double timber door |  |  |  | no | 12000
|  |  | Single glass door |  |  |  | no | 25000
|  |  | Double glass door |  |  |  | no | 35000
|  |  | Balcony bi-folding door |  |  |  | m2 | 10000
|  |  | Roller shutter |  | 1h frr |  | m2 | 8000
Finishes
|  | External wall finishes | [6 empty] | 500
|  |  | Waterproof |  |  |  | m2 | 300
|  |  | Stone cladding |  | PC rate 2000/m2 |  | m2 | 3000
|  |  | External tile |  | PC rate 400/m2 |  | m2 | 600
|  |  | External paint |  |  |  | m2 | 250
|  |  | Architectural features |  |  |  | item | 10% |  | allowance only
|  | Roof finishes |  |  |  | roof = building footprint |  |  | 100
|  |  | Insultion |  |  |  | m2 | 300
|  |  | Waterproof |  |  |  | m2 | 300
|  |  | Tile w screed |  | PC rate 400/m2 |  | m2 | 600
|  |  | Channel |  |  |  | item | 100000 |  | allowance only
|  |  | Skirting |  |  |  | item | 10% |  | allowance only
|  | Balcony finishes | [6 empty] | 150
|  |  | Waterproof |  |  |  | m2 | 300
|  |  | Tile w screed |  | PC rate 600/m2 |  | m2 | 800
|  |  | Typhoon proof aluminium ceiling |  |  |  | m2 | 5000
|  |  | Glass balustrade |  | 1100mm high |  | m | 9000
|  |  | Metal railing |  | 1100mm high |  | m | 3000
|  | Floor finishes |  |  |  | residential: 0.8m2/m2 CFA |  |  | 800
|  |  | Waterproof |  |  |  | m2 | 300
|  |  | Tile w screed |  | PC rate 600/m2 |  | m2 | 800
|  |  | Stone w screed |  | PC rate 2000/m2 |  | m2 | 3000
|  |  | Timber floor |  | PC rate 1200/m2 |  | m2 | 2000
|  |  | Vinyl / carpet |  | PC rate 300/m2 |  | m2 | 600
|  |  | Raised floor system |  |  |  | m2 | 6000
|  |  | Stone threshold |  |  |  | m | 1000
|  |  | Skirting |  |  |  | item | 10% |  | allowance only
|  | Internal wall finishes | [6 empty] | 2500
|  |  | Waterproof |  |  |  | m2 | 300
|  |  | Paint |  |  |  | m2 | 250
|  |  | Tile w screed |  | PC rate 600/m2 |  | m2 | 800
|  |  | Stone w screed |  | PC rate 2000/m2 |  | m2 | 3000
|  |  | Stone window cill |  |  |  | m | 1000
|  |  | Wallpaper |  | PC rate 300/m2 |  | m2 | 600
|  |  | Laminate / veneer |  |  |  | m2 | 1400
|  |  | Glass |  | PC rate 500/m2 |  | m2 | 1400
|  | Ceiling finishes | [6 empty] | 600
|  |  | Open ceiling paint |  |  |  | m2 | 300
|  |  | Aluminium ceiling panel |  |  |  | m2 | 1100
|  |  | Gypsum board ceiling w paint |  |  |  | m2 | 900
|  |  | Baffle ceiling w paint |  |  |  | m2 | 1600
|  |  | Bulkhead and sides of beams |  |  |  | item | 20% |  | allowance only
|  | Lift finishes |  |  |  |  | Lift | 100000 | 20 | allowance only
| Fixtures and fittings | [7 empty] | 800
|  | Sanitary fittings |  |  | 1 bathroom 1 kitchen |  | flat | 30000
Cabinet
|  |  | Bathroom cabinet |  |  |  | set | 40000
|  |  | Kitchen cabinet |  | open kitchen |  | set | 65000
[5 empty] | enclosed kitchen |  | set | 35000
|  | Shower partition |  |  | 2.5x2.5m |  | set | 18000
|  | Toilet cubicle |  |  |  |  | set | 12000
|  | Steel and metal works |  |  |  | residential area | m2 | 500
|  | Décor, graphics and signage |  |  |  |  | item | 200000 |  | allowance only
External and Landscaping Works | [8 empty] | 600
| Hard Landscape | [5 empty] | m2 | 8000
|  | Driveway and conrete paving |  |  |  |  | m2 | 1000
|  | Stone pavement |  |  |  |  | m2 | 3000
|  | Timber decking |  |  |  |  | m2 | 4000
|  | Planter wall |  |  |  |  | m | 4000
|  | Fence wall |  |  |  |  | m2 | 12000
|  | Vertical green wall |  |  |  |  | m2 | 4000
| Soft Landscape | [5 empty] | m2 | 4000
| Outdoor swimming pool | [5 empty] | m2 | 35000
| Canopy | [5 empty] | m2 | 40000
| Footbridge | [5 empty] | m | 100000
| Covered walkway | [5 empty] | m2 | 25000
| External lighting (façade & landscape) | [5 empty] | item | 5M |  | allowance only
| Underground drainge |  |  |  |  | site area | m2 | 200
| Utilities devision | [5 empty] | item | 0.5-2M |  | allowance only
E&M Services | [8 empty] | 8000 | consider MC attendance
Lift and Escalator
|  | Lift for low rise |  |  |  |  | no | 1.2M
|  | Lift for high rise |  |  |  |  | no | 2.2M
|  | Escalator |  |  |  |  | no | 1.2M
| Electrical Installation |  |  |  |  | CFA | m2 | 3200 |  | residential
| MVAC Installation |  |  |  |  | CFA | m2 | 2400 |  | residential
| Fire Services Installation |  |  |  |  | CFA | m2 | 800 |  | residential
| Plumbing and Drainage Installation |  |  |  |  | CFA | m2 | 1800 |  | residential
| Gas Installation | [5 empty] | flat | 40000 |  | residential
| Filtration system for swimming pool | [5 empty] | item | 9M |  | 250m2 pool
| Building Maintenance Unit (BMU) | [5 empty] | tower | 500000
| BWIC | [5 empty] | item | 5%
Other
| Kitchen appliance | [5 empty] | flat | 50000
| Concrete spalling repair (A&A) |  |  |  |  | CFA | m2 | 50
| Refuge floor | [5 empty] | m2 | 12000
| Clubhouse | [5 empty] | m2 | 40000
| BEAM Plus | [5 empty] | item | 2%
| Design and Build | [5 empty] | item | 5-10%
| Congested site | [5 empty] | item | 5%
Preliminaries |  |  |  |  | might include in breakdown |  | item | 12% | 4000
Contingencies | [6 empty] | item | 10% | 2000
Fluctuation
[9 empty] | 36520 | Apartment, high rise, high end
internal wall : floor ratio =
residential 1m2/m2
office 0.5m2/m2
hotel 1.5m2/m2
facade ratio =
Residential 1.2m2/m2
office / hotel 0.4m2/m2
industrial 0.4m2/m2
window/curtain wall: external wall finish =
20% / 80%

## VE Effect
VE Effect Case Study
Element |  | Super-high-rise and less tower no. (1999) |  | Increase floor height (2004 Q1B) |  | Add bay window (1999 Q1) |  | Office to serviced apartment (2004 Q1A) |  | Add indoor swimming pool (2004 Q1B) |  | Single block to two half height (2008 Q1.1.3) |  | Coaster in shopping mall (2005 Q4.B) |  | One block to two slender blocks (2012 D1Q1) |  | Add escalator and renovate foyer (2018 D1Q1) |  | Add footbridge for 2 existing bld (2018 D1Q1) |  | Steel structure indirect impact (2018 D1Q2b) |  | Add one lift (2022 D1Q1b) |  | Two office floors to exhibition (2024 D1Q1) |  | Slender L to whole block with larger footprint |  | Sub-division of units |  | Industrial to office |  | Renovate: Godown to office |  | Large flat to smaller flat
|  | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason | $/CFA | Reason
CFA / design |  | increase CFA | refuge floor |  | refuge floor may be required |  |  |  | floor height; pipe duct & plant room |  | increase floor height (see other part); reduce guestroom for pool; changing room, toilet, plant room; acoustic provision |  | refuge floor not required |  | emergency escape access and rescue facilities; safety net; storage space for shuttle coaster; plant room, control room; passenger loading and unloading bay; acoustic provision | increase CFA | [5 empty] | increase CFA | thinner structural elements
Demolition & Hoarding | [18 empty] | break up slab to form escalator void - smaller pit at G/F, bigger void at 1&2/F (coring or saw cutting, provision of temporary structting; remove existing services and finishes |  | façade opening | [13 empty] | demolition of façade, internal wall, IFO, E&M
Foundation and Basement |  | ↑? | strengthen - load, wind load, slenderness; greater dead load from new structure design; settlement control; less number of tower; check with E | ↑ | strengthen - load and wind load, slenderness; greater dead load from new structure design |  |  | ↑? | strengthen - load; check with E | ↑ | strengthen - load from pool; greater dead load from new structure design |  |  |  | strengthen - load; greater dead load from new structure design | ↑ | strengthen for slender - wind effect; greater dead load from new structure design; cluster of foundation and pile cap - increase formwork to concrete ratio; increase pile test number; basement change |  | consider effect on existing substructure |  | modification to existing building if any |  | lighter as overall building weight is lighter |  | loading on substructure | ↑ | increase loading | ↓ | improve piling efficiency - larger diameter & more choice; increase pile cap / footing footprint | ↑ | strenthen for load increase | ↑? | possible strengthening; check with E |  | assume underpinning not required | ↑ | loading increase
Superstructure
| Structure | ↑ | (increase volume, grade, steel ratio) strengthen - load, wind load, slenderness | ↑ | strengthen - load and wind load, slenderness | ↑ | suspended concrete slabs to top and bottom; formwork; reinforcement | ↑? | fewer but bigger column -> more but leaner column / wall; loading | ↑ | strengthen - load from pool; structure for design change | ↑ | independent transfer plate |  | strengthen - load | ↑ | strengthen for slender - wind effect; increase ratio of structural wall for lift shaft; increase staircase |  | escalator pit in G/F and pit in 1&2/F slab; structural strengthing |  | structure strengthing to existing building; footbridge structure - prefab / in-situ, concrete / steel, column on street or not; staircase |  | metal descking interface with beam / columns need careful design to void variation; opening to steel member fixed before prefabrication |  | loading on structure extended lift shaft walls and dividing walls hoisting beam, separator beams if no dividing walls, lift pit, lift pit sides and bottom, excavation roof slabs, machine bases | ↑ | omit on level of floor slab and beam; retain lift shaft and staircase; add lift shaft and escalator voids; longer column and walling space; transfer structure; floor and slab strengthened, hoisting and hanging structure | ↓ | building efficiency increase; reduce service core ratio; reduce strength of structure - smaller volume ratio and steel ratio, less slender | ↑ | strenthen for load increase | ↑ | form opening for escalator at lift lobby floor; extra lift shaft |  | assume strengthening not required | ↑ | loading increase
| Façade | ↑ | difficulty of construction; glass thickness for wind load; depend on external wall to floor ratio | ↑ | window load, glass thickness; façade area |  | window panel | ↓ | Façade design | ↑ | possible glazed enclosure | ↑ | more façade area |  |  | ↑ | increase external wall to floor ratio | [8 empty] | ↑ | more glass wall upgrade design of G/F façade main entrance enlarged for more ppl flow | ↓ | reduce facade ratio, more regular shape | ? | remain unchanged; some kitchen / toilet might not have window | ↑ | more curtain wall and window for natural light |  | new curtain wall
| Internal wall |  |  | ↑ | wall height |  |  | ↑ | add substantial amount of internal partition and door; pipe duct & plant room | [9 empty] | parittion with door (consider high ceiling height, FRP) |  |  |  | more non-structural wall | [6 empty] | ↑ | more partition to divide units | ↑ | extra block wall for office compartment; extra RC wall for corridor |  | new internal wall | ↑ | more internal wall for smaller size flat and increase flat number
| Door and shutter | [17 empty] | smoke curtain or fire shutter to escalator voids |  | fire shutter; glass door to footbridge | [9 empty] | door may not increase as small units are usually studio |  |  |  | new door and shutter | ↑ | more door for increased flat number
Finishes
| External wall finishes | ? | depend on external wall to floor ratio | ↑ | façade area | ↑ | external tile finishes |  |  |  |  | ↑ | more façade area | [7 empty] | special provision for façade of existing building | [6 empty] | ↓ | reduce facade ratio, more regular shape |  |  | ↑? | better external wall finish; less fininsh area for enlarged curtain wall area |  | new external wall finishes | ↑ | possible more window area
| Roof finishes | ↓ | reduce number of roof | [8 empty] | ↑ | independent roof |  |  | ↑ | more channels and skirtings |  |  |  | roofed or not, green roof, finish to roof
| Balcony finishes | [34 empty] | ↑ | more balcony area
| Interior finishes |  |  | ↑ | wall height | ↑ | internal plaster finishes; granite slab window sill and backing | ↑ | add substantial amount of toilet; change of internal finishes from office area with bare finishes to serviced apartment with full finishes: IFO for common areas e.g. clubhouse; BOH provision including areas for house keeping, laundry, ironing, kitchen, etc. | ↑ | IFO for design change | ↑ | independent main entrance lobby |  |  | ↑ | more lift lobbies; clubhouse |  | floor, wall, ceiling finish to foryer |  | finishes to footbridge floors, walls, columns, ceilings and underside of the footbridge: renovation of existing building connected foyer |  | more floor, wall, ceiling finishes area as structural delement is thinner |  | wall finisehs to increased wall areas lift machine room finishes finishes at enlarged lift lobbies omit finishes of ceiling and floor for omitted floor slab at enlarged lift shaft lift IFO | ↑ | more movable partition, fewer but heavier door, more expensive finishes, more expensive fixed or loose furniture; upgrade entrance, lobbies, staircase and toilet; acoustic treatment; catwalk or steel platform for maintenance; additional signage; add kitchen and eating space, seating, access for special guest |  |  | ↑ | Floor: more finish to toilet and kitchen (tile); less finish to bedroom and living room (wood flooring); total floor finish area unchanged Wall: more wall finish area | ↑ | IFO for lift lobby and corridor; IFO for lift; more toilet on each floor |  | IFO for lobby and tenant area | ↑ | higher internal wall to floor ratio
| Fixtures and fittings | [6 empty] | ↑ | built-in fixtures for pantry, storage cabinet, basin & mirror cabinet; sanitary for toilets | ↑ | built-in furniture for design change; sanitary for toilet | [7 empty] | railing to escalator voids with curbs |  | railing; gutter, surface channel |  | hanger for architectural works and E&M works with fireproof coating |  | cat ladder |  |  |  |  | ↑ | more basin cabinet as bathroom number increase; more letter box; sanitary more quantity but lower quality | ↑ | signage; sanitary for toilet |  | new sanitary | ↑ | more cabinets, sanitary for increased flat number
External and Landscape |  | ↑ | larger external area |  |  |  |  | ↑ | underground drainage for addition of toilets; tourist bus lay-by are for loading and unloading | ↑ | underground drainage for water discharge | ↓ | less external works |  |  | ↓ | less external area | [8 empty] | ↑ | access road, carpark, signagne for more ppl flow; capacotu of underground mains increase | ↓ | reduce external area |  |  | ↑ | better finish, external lighting, dropoff area, green roof |  | external lighting
E&M Services
| Lift & Escalator | ↑ | lift number; travel distance; faster speed for higher zone | ↑ | travel distance; faster speed for higher zone |  |  | ↑ | lift number and allocation; addition of service lift |  |  | ↑ | independent sets of lift, lift shafts, lift machine rooms |  |  | ↑ | number of lift |  | escalator | [5 empty] | lift | ↑ | might add |  |  | ↑ |  | ↑ | travel speed |  | lift modernization or replacement | ↑ | more lift for more flat number
| EL, MVAC, FS, PD, Gas | ↑ | vertical elements increase; design more complicated MVAC: higher performance PD: larger pipe size & powerful pump to support same flow rate; heavier duty valves EL: more electrical loading requirement on main and sub-main distribution system; higher rating of transformer | ↑ | vertical elements increase; design more complicated MVAC: cooling capacity for increased room volume; higher performance FS: addition of sprinkler provision, fire detection system PD: larger pipe size & powerful pump to support same flow rate; heavier duty valves EL: more electrical loading requirement on main and sub-main distribution system; higher rating of transformer |  |  | ↑ | EL: revise EL & ELV system; revise electrical loading; security system; revise lighting and power system MVAC: ventilation for toilet and pantry; revise cooling load & chiller provision FS: sprinkler and AFA provision PD: add substantial amount of toilet; pipe size and arrangement; hot water | ↑ | PD: pipeworks; water tank size; PD for changing room and toilet MVAC: increase ventilation for pool area and wet area EL: lighting for indoor pool | ↑ | independent building services ductworks, main plant |  | additional E&M EL: extra electricity power; special lighting and background music FS: FS provision | ↑ | more equipment; E&M for lift lobbies; water tank, pump room and lift machine room |  | lighting and power, air conditioning, fire sprinkler, public address, CCTV |  | MVAC and FS if fully closed normal EL & FS provision (depend on distance from main services in existing building) |  |  |  | pit drain electrical supply to lift and lift landing call panel slight effect on fire services | ↑ | MVAC: higher cooling capacities, higher air exchange rate; acoustic requirement EL: higher capacity and moveable power distribution; flexible lighting system with programmed control system and dimmer; audio-visual system; more advanced IT and communication infrastructure PD; enhance for more toilet and kitchen |  |  | ↑ | MVAC: more air-conditioning EL: power distribution system; more lighting provision PD: more pipeworks for toilet FS: sprinkler for open kitchen | ↑ | PD: PD works for more toilets EL: security system; ELV provision for office MVAC: higher performance AC instead of mechnical ventilation FS: sprinkler system, fire shutter |  | EL upgrade main plant loading, provide light fittings to tenant areas ELV add BMS, security, etc. PD more toilets and water supply to pantry FS system based on new layout MVAC central A/C | ↑ | more E&M arrangement for increased flat number including power distribution, lighting and power point, air conditioning equipment, and plumbing and drainage pipeworks, etc.
| BWIC | ↑ | pro-rata | ↑ | pro-rata |  |  | ↑ | pro-rata | ↑ | pro-rata | ↑ | pro-rata |  |  | ↑ | pro-rata | [7 empty] | V |  |  |  |  | ↑ | pro-rata | ↑ | pro-rata |  | pro-rata | ↑ | pro-rata
| Other | [7 empty] | town gas provision | ↑ | pool filtration plant; heated or cold water only | ↑ | independent BMU |  | permanent maintenance platform | [5 empty] | special lighting and advertising sign | [8 empty] | ↑ | more gas provision
Other | [8 empty] | FF&E for loose furniture, decoration, etc.; appliances - fridge, TV, cooking range | ↑ | pool equipment | [11 empty] | early procurement to engage specialist and allow long lead time; early freezing of design; faster proframme but concrete core & casing on critical path may drag the programme; special cranes | [6 empty] | ? | kitchen appliance more quantity but lower quality | ↑ | gondola; more parking spaces |  | gondola
Preliminaries |  |  | efficiency of labour; vertical transportation; scaffolding | ↑ | pro-rata; transportation for labour and plant; safety factor and management cost; scaffolding | ↑ | pro-rata | ↑ | pro-rata |  |  | ↑ | concurrent work - save time related prelim; more tower crane; more congested site area - relocation of site office and storage area |  | insurance premium for extensive installation at height; temporary high level erection platform; special hoisting facilities; special protection; testing and commissioning | ↑ | pro-rata |  | 10-15%; consider temporary protection, working platform, traffic diversions, excavation permit |  | statutory approval for planning, bridge and traffic; traffic diversion; night work for hoisting |  |  |  | V | ↑ | corresponding increase |  | reduced area for site storage, in-situ fabrication, logistics and site office - extra cost for Prelim |  |  | ↑ | pro-rata |  |  | ↑ | pro-rata
Contingency | [18 empty] | 10% | [5 empty] | V | ↑ | corresponding increase | [8 empty] | ↑ | pro-rata
Overall |  | ↑ |  | ↑ |  | ↑ |  | ↑ |  | ↑ |  | ↑ |  |  |  | ↑
↑
↓

## types
new building on vacant site | residential |  | school |  | lift shaft
new building with demolition of existing |  | residential portion |  | acoustic | basement
A&A to existing building |  | lobby | exhibition hall |  | foundation and els
|  | clubhouse |  | 2024 D1Q2 | flat unit
|  | sky garden | footbridge |  | escalator
|  | swimming pool | elderly centre |  | roof extension
|  | gas | hospital |  | add / omit staircase
hotel / serviced apartment
guestroom
clubhouse
laundry room
lobby
CCTV, telephone
shopping mall
tenant area
lobby
escalator
CCTV, audio system
office
tenant area
lobby
acoustic for meeting room
door access system, CCTV
carpark
carpark system

## VE Effect (Blank)
Element
|  | $/CFA | Reason
CFA / design
Demolition & Hoarding
Foundation and Basement
Superstructure
Structure
Façade
Internal wall
Door and shutter
Finishes
External wall finishes
Roof finishes
Balcony finishes
Interior finishes
Fixtures and fittings
External and Landscape
E&M Services
Lift & Escalator
EL, MVAC, FS, PD
BWIC
Other
Other
Preliminaries
Contingency
Overall
↑
↓